## UAT Report
User Acceptance Testing (UAT) Report
Test Summary
Module | Total Test Cases | Passed | Failed
Module Login/Signup | 13 | 13 | 0
Module Cart | 25 | 21 | 2
Module Checkout and Order confirmation | 38 | 34 | 2
Defect Summary
Test Case ID | Title | Module | Expected Result | Actual Result | Priority
TC_CART_05 | Verify adding large value to product quantity | Shopping Cart | A message should be shown that maximum quantity allowed is 1000 | A message is shown that maximum product quantity is 10000 | P0
TC_CART_07 | Verify user cannot checkout with exceeded product quantity | Shopping Cart | Checkout should be disabled or show appropriate message | Checkout button is enabled | P0
TC_CHECKOUT_013 | Verify email confirmation is sent after order | Checkout | Email with order summary and confirmation should be received | Confirmation email not received | P2
UAT Sign-off
Tester Name | Sign-off Date | Status | Remarks
Somya Agarwal | 2025-06-24 | Partially Completed | All critical functionalities tested.